## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Problems of online shopping | 2 | 5 | 2 | 4 | 100%
Refine the real problem | 3 | 3 | 3 | 3 | 100%
Functional prototype specifications | 3 | 4 | 3 | 4 | 100%
Login Dialog | 5 | 4 | 0 | 0 | 0%
Display top 3 most popular products | 5 | 4 | 0 | 0 | 0%
User greetings of login user | 5 | 4 | 0 | 0 | 0%
Display of Monthly Special | 5 | 4 | 0 | 0 | 0%
Input validation | 7 | 1 | 0 | 0 | 0%
Daily login records | 7 | 3 | 0 | 0 | 0%
Last viewed item | 7 | 5 | 0 | 0 | 0%
Create Feedback form - C | 7 | 1 | 0 | 0 | 0%
View all feedback by users - R | 7 | 3 | 0 | 0 | 0%
Allow users to edit feedback before submitting - U | 7 | 3 | 0 | 0 | 0%
Clear all feedback - D | 7 | 6 | 0 | 0 | 0%
Email confirmation | 9 | 3 | 0 | 0 | 0%
Language preference | 9 | 6 | 0 | 0 | 0%
Add User's interest of Product | 9 | 3 | 0 | 0 | 0%
Refence code benefit | 9 | 4 | 0 | 0 | 0%
Indication of interest for being a seller or buyer | 11 | 5 | 0 | 0 | 0%
Security questions | 11 | 2 | 0 | 0 | 0%
Region preference | 11 | 6 | 0 | 0 | 0%
Connect to your social media | 12 | 1 | 0 | 0 | 0%
Create a page for users to register their membership with our website - C | 13 | 5 | 0 | 0 | 0%
Retrieve member information to make sure that there is no duplicate member(Administration) - R | 14 | 8 | 0 | 0 | 0%
Update member information like home address, handphone number and email address(Administrator) - U | 14 | 7 | 0 | 0 | 0%
Delete member information upon deactivating account - D | 14 | 4 | 0 | 0 | 0%
Adaptive searching | 15 | 5 | 0 | 0 | 0%
Filter search | 15 | 7 | 0 | 0 | 0%
Item manufacture preference | 15 | 4 | 0 | 0 | 0%
Top items that friends frequently search | 15 | 5 | 0 | 0 | 0%
Recommendations from friends | 15 | 6 | 0 | 0 | 0%
Voice search activation | 15 | 4 | 0 | 0 | 0%
Create a page for seller to upload products to sell - C | 17 | 5 | 0 | 0 | 0%
Search by pictures - R | 17 | 6 | 0 | 0 | 0%
Update most popular/new product - U | 17 | 5 | 0 | 0 | 0%
Delete unwanted product - D | 17 | 3 | 0 | 0 | 0%
Users need to rekey in password before proceed to checkout | 18 | 5 | 0 | 0 | 0%
Verification Security questions need to be answered | 18 | 6 | 0 | 0 | 0%
In-store Discount code input(E.g Input In-store code for $5 off when there is a minimum expenditure of $30) | 18 | 7 | 0 | 0 | 0%
Total amount of all the items | 20 | 5 | 0 | 0 | 0%
Create shopping cart - C | 20 | 4 | 0 | 0 | 0%
Overview of all items added into the shopping cart Overview of total price of all items in the shopping cart Recommendation tab(E.g other users also view this product) - R | 20 | 5 | 0 | 0 | 0%
Able to add items into the shopping cart - U | 20 | 3 | 0 | 0 | 0%
Able to delete one item or many items in the shopping cart with a single click - D | 20 | 6 | 0 | 0 | 0%
Captcha input feature at confirmation page | 21 | 5 | 0 | 0 | 0%
Payment preference | 21 | 4 | 0 | 0 | 0%
Shipping Preference(Choice of express shipping, standard shipping or meet up) | 21 | 6 | 0 | 0 | 0%
Requests for special service (E.g bubble wrap item) | 22 | 2 | 0 | 0 | 0%
Option for additional Insurance to insure lost delivery item. | 23 | 3 | 0 | 0 | 0%
Product add on( E.g user purchase airpods, then website shows available add on for the product you purchase) | 23 | 4 | 0 | 0 | 0%
Create payment info page for users - C | 24 | 5 | 0 | 0 | 0%
One time password for payment preference (through email or phone number) - R | 24 | 6 | 0 | 0 | 0%
Able to update delivery destination or payment details - U | 24 | 4 | 0 | 0 | 0%
Able to cancel shopping cart confirmation - D | 24 | 5 | 0 | 0 | 0%
Administrator – Members Management Page | 25 | 4 | 0 | 0 | 0%
Products Management (edit of product desc ect) | 25 | 5 | 0 | 0 | 0%
Sales revenue | 25 | 3 | 0 | 0 | 0%
inventory of products | 26 | 3 | 0 | 0 | 0%
Top Sales | 26 | 5 | 0 | 0 | 0%
Total number of members | 26 | 6 | 0 | 0 | 0%
Order status | 27 | 2 | 0 | 0 | 0%
Logistic tracking | 27 | 7 | 0 | 0 | 0%
Users feedbacks on shopping experience | 27 | 4 | 0 | 0 | 0%
Create a page for the admin to handle the administrator part - C | 29 | 4 | 0 | 0 | 0%
Retrieve data about which product was being sold most and then display it.(Top sales) - R | 29 | 5 | 0 | 0 | 0%
Update product inventory upon purchase or refund by customer - U | 29 | 3 | 0 | 0 | 0%
Delete products that are no longer for sales by our page - D | 29 | 2 | 0 | 0 | 0%